Project Management Practice Test

# February 2007

## Name__________________________________________

- Calculate the estimated times and variances for each activity below.

T=( A +4M + B)/6               V = ((b-a)/6)2

| Activity | IP | A | M | B | Expected Time | Variance |
| --- | --- | --- | --- | --- | --- | --- |
| A | --- | 3 | 4 | 5 |  |  |
| B | --- | 3 | 5 | 7 |  |  |
| C | --- | 2 | 3 | 7 |  |  |
| D | A | 4 | 4 | 4 |  |  |
| E | B | 2 | 3 | 7 |  |  |
| F | C | 5 | 6 | 13 |  |  |
| G | C | 1 | 4 | 7 |  |  |
| H | E,F | 4 | 4 | 4 |  |  |
| I | D,H | 1 | 3 | 8 |  |  |
| J | G | 2 | 4 | 6 |  |  |
| K | I,J | 4 | 4 | 4 |  |  |

- Fill out the following information for the project above.

| Activity | T | ES | EF | LS | LF | S | CP |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A |  |  |  |  |  |  |  |
| B |  |  |  |  |  |  |  |
| C |  |  |  |  |  |  |  |
| D |  |  |  |  |  |  |  |
| E |  |  |  |  |  |  |  |
| F |  |  |  |  |  |  |  |
| G |  |  |  |  |  |  |  |
| H |  |  |  |  |  |  |  |
| I |  |  |  |  |  |  |  |
| J |  |  |  |  |  |  |  |
| K |  |  |  |  |  |  |  |

- Draw the network.

- What is the estimated time of completion of the project?

- What is the critical path for this project?

- What is the probability that this project will be completed in 29 weeks? Z = C-T/(

- What is the probability that this project will be completed in 32 weeks?