Project Management Practice Problem 1

## Name__________________________________________

- Calculate the estimated times and variances for each activity below.

T=( A +4M + B)/6               V = ((b-a)/6)2

| Activity | IP | A | M | B | Expected Time | Variance |
| --- | --- | --- | --- | --- | --- | --- |
| A | --- | 6 | 8 | 16 |  |  |
| B | --- | 12 | 16 | 20 |  |  |
| C | --- | 8 | 14 | 20 |  |  |
| D | ABC | 9 | 20 | 25 |  |  |
| E | ABC | 7 | 8 | 9 |  |  |

- Fill out the following information for the project above.

| Activity | T | ES | EF | LS | LF | S | CP |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A |  |  |  |  |  |  |  |
| B |  |  |  |  |  |  |  |
| C |  |  |  |  |  |  |  |
| D |  |  |  |  |  |  |  |
| E |  |  |  |  |  |  |  |

- Draw the network.

- What is the estimated time of completion of the project?

- What is the critical path for this project?

- What is the probability that this project will be completed between 33 and 38 weeks? Z = C-T/(