Project Management Practice Problem 2

## Name__________________________________________

- Calculate the estimated times and variances for each activity below.

T=( A +4M + B)/6               V = ((b-a)/6)2

| Activities | Immediate Predecessor | aj | mj | bj | Expected Time | Variance |
| --- | --- | --- | --- | --- | --- | --- |
| A | - | 2 | 4 | 6 | 4 | .4444 |
| B | - | 6 | 8 | 10 | 8 | .4444 |
| C | A | 1 | 5 | 15 | 6 | 5.4444 |
| D | C | 1 | 5 | 9 | 5 | 1.777 |
| E | B | 6 | 8 | 10 | 8 | .4444 |

.8888     sqrt=.943

- Fill out the following information for the project above.

| Activity | T | ES | EF | LS | LF | S | CP |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A | 4 | 0 | 4 | 1 | 5 | 1 |  |
| B | 8 | 0 | 8 | 0 | 8 | 0 | * |
| C | 6 | 4 | 10 | 5 | 11 | 1 |  |
| D | 5 | 10 | 15 | 11 | 16 | 1 |  |
| E | 8 | 8 | 16 | 8 | 16 | 0 | * |

- Draw the network.

- What is the estimated time of completion of the project?

16

- What is the critical path for this project?

BE

- What is the probability that this project will be completed in less than 14 days? Z = C-T/(

16-14/.943=2.12=.4830

.5 - .4830 = .017 %