Project Management Practice Problem 3

## Name__________________________________________

- Calculate the estimated times and variances for each activity below.

T=( A +4M + B)/6               V = ((b-a)/6)2

| Activity | IP | A | M | B | Expected Time | Variance |
| --- | --- | --- | --- | --- | --- | --- |
| A | --- | 3 | 5 | 13 |  |  |
| B | A, | 2 | 6 | 13 |  |  |
| C | A, | 5 | 9 | 19 |  |  |
| D | A, | 3 | 4 | 5 |  |  |
| E | B | 6 | 7 | 8 |  |  |
| F | C,D | 2 | 10 | 27 |  |  |
| G | C,D | 4 | 8 | 15 |  |  |
| H | E | 4 | 8 | 15 |  |  |
| I | E | 4 | 8 | 15 |  |  |
| J | H | 5 | 6 | 7 |  |  |
| K | I | 6 | 7 | 8 |  |  |
| L | F | 9 | 10 | 11 |  |  |
| M | G | 1 | 2 | 3 |  |  |
| N | J,K | 4 | 5 | 6 |  |  |
| O | L,M | 5 | 9 | 19 |  |  |

- Fill out the following information for the project above.

| Activity | T | ES | EF | LS | LF | S | CP |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A |  |  |  |  |  |  |  |
| B |  |  |  |  |  |  |  |
| C |  |  |  |  |  |  |  |
| D |  |  |  |  |  |  |  |
| E |  |  |  |  |  |  |  |
| F |  |  |  |  |  |  |  |
| G |  |  |  |  |  |  |  |
| H |  |  |  |  |  |  |  |
| I |  |  |  |  |  |  |  |
| J |  |  |  |  |  |  |  |
| K |  |  |  |  |  |  |  |
| L |  |  |  |  |  |  |  |
| M |  |  |  |  |  |  |  |
| N |  |  |  |  |  |  |  |
| O |  |  |  |  |  |  |  |

- Draw the network.

- What is the estimated time of completion of the project?

- What is the critical path for this project?

- What is the probability that this project will be completed in less than 45 weeks? Z = C-T/(

- What is the probability that this project will be completed by 50 weeks?